## Slide 1
Based on PM² v3.1
PM² Essentials Training Material

## Slide 2: Copyright
© European Union, 2024
PM² is an open-source project management methodology created and supported by the European Commission.
Reproduction and reuse is authorized provided the source is acknowledged.
The PM² logo is the property of the European Union and may not be registered as a trademark or otherwise, nor used separately from these documents.
Neither the publication nor the logo can be used in a way which suggests endorsement of an external organization by the European Union.

## Slide 3: Introduction

## Slide 4: The European Commission's Project Management Methodology

## Slide 5: Objectives
This course introduces the PM² Methodology of the European Commission.
It enables participants to:
  obtain the foundation knowledge necessary for using effectively the PM² Project Management Methodology.
  understand the full PM² project life cycle, organisation, roles & responsibilities.
  understand the PM² Mindsets.
  Familiarise themselves with the key PM² Artefacts for initiating, planning, executing, controlling and closing projects.

## Slide 6: Course Content
Introduction
Project (Management) basics
PM² Overview
Project Governance
Phases and Artefacts
PM² Mindsets

## Slide 7: Suggested Course Schedule
Session 1
09:00 Kick-off
09:15 Project (Management) Basics
10:30 Introduction to PM²
11:00 Break
11:15 Governance of Projects
11:45 PM2 Mindsets
12:00 Initiating Phase
12:30 Lunch
Session 2
13:30 Planning Phase
14:00 Executing Phase
14:30 Monitor & Control
15:15 Break
15:30 Monitor & Control (cont’d)
16:15 Closing Phase
16:45 Wrap-up
17:00 End course

## Slide 8: Contact the Methodology Office
European Commission
DG for Digital Services
DIGIT A2.001 – Procurement & Programme Management Solutions
Methodologies Office
Contacts:
Email: EC-Methodologies@ec.europa.eu
Website: pm2.europa.eu
JoinUp: joinup.ec.europa.eu

## Slide 9: Project (management) Basics

## Slide 10: What is a Project?
A project is a temporary organisation which is set up to create a unique output (product or service). A project is defined by its unique scope, time, cost, and quality objectives.

## Slide 11: Constraints of a Project
constraints
Schedule
Resources
Budget
Quality
Scope
Risk

## Slide 12: Project Outputs, Outcomes, Benefits
Project deliverables or outputs are merely a means to an end.
The real purpose of a project is to achieve given outcomes that will yield measurable benefits.
Note that project outcomes and benefits are often realised only after the project has closed.

## Slide 13: Why do we do Projects?
Projects deliver Outputs (deliverables) that deliver a change (social, commercial, operational, etc.)
These changes generate outcomes for the beneficiaries or users.
On the long term these outcomes produce benefits or impact.
These benefits realise or support the organisation strategy.
Outputs
Changes
Outcomes
Benefits/Impact

## Slide 14: Portfolio, Programme, Project Relationship
Operations
(Everyday Work)
Strategic Objectives
Strategic Planning
Portfolio Management
Programme Management
Project Management
Main Artefacts
Business Strategy
Strategy Implementation Plan
Portfolio Analysis & Reports
Business Case
Project Charter
Project Plans
Progress Reports

## Slide 15: Examples of Projects
Projects are undertaken at all levels of the organisation and they can involve 2-3 persons or many thousands.
Their duration ranges from 4-5 weeks to several years. Projects can involve one or many organisational units.
Developing a new product or service
Effecting a change in structure, staffing, or style of an organization
Designing a new transportation vehicle
Developing, modifying or acquiring a new information system
Constructing a building or facility
Building a water system for a community
Running a campaign for political office
Implementing a new business procedure or process
Responding to a contract solicitation.

## Slide 16: Competences
People Competences | Perspective Competences
Self-reflection and self-management Personal integrity and reliability Personal communication Relationships and engagement Leadership Teamwork Conflict and crisis management Resourcefulness Negotiation Results orientation | Strategy Governance, structures and processes Compliance, standards and regulations Power and interest Change and transformation Culture and values Source: IPMA-ICB (adapted)

## Slide 17: Personal and Professional Virtues

## Slide 18: PM² Overview

## Slide 19: The Purpose of PM²
The purpose of PM² is to enable Project Managers to deliver solutions and benefits to their organisations by effectively managing the entire lifecycle of their project

## Slide 20: The PM² Methodology

## Slide 21: The House of PM²

## Slide 22: PM² Mindsets
The PM² Mindsets enable us to apply the Methodology more effectively and help us navigate through the complexities of project reality.
PM² Processes
PM² Processes & Mindsets

## Slide 23: PM² Project Lifecycle
Effort
Time
Planning
Initiating
Planning
Executing
Closing
Monitor & Control

## Slide 24: PM² Phases
 | PM² Phases | Description
1 | Initiating | Get the project off to a good start.
2 | Planning | Define deliverables, verify the Business Case, plan work, etc.
3 | Executing | Create the project’s deliverables.
4 | Closing | Deliverables validation, lessons learnt, project closure.
 | Monitor & Control: | The Project Manager (PM) monitors & controls the work, risks, issues, quality, etc. throughout the whole project lifecycle.

## Slide 25: PM² Project Lifecycle - Phases & Drivers
Project
Owner (PO) initiates
Business Case
Project Initiation Request
Initiating
Define Scope
Assign PM
Project Charter
RfP
Project
Manager (PM)
plans
Project
Charter
Planning
Elaborate Scope
Assign PCT
Project Handbook & Project
Work Plan
RfE
Project
Core Team (PCT)
executes
Project
Work Plan
Executing
Manage Scope
Coordinate
Project
Deliverables
RfC
Project
Stakeholders evaluate
Project
Deliverables
Closing
Capture Lessons
Accept Project
Project-End Report
Project
Drivers
Phase
Inputs
Phase
Outputs
Project
Phases
Phase Gates Approvals
Monitor & Control

## Slide 26: Phase Gates / Approvals
These check points contribute to the overall project management quality.
The three PM² (approval) Phase Gates are:
  RfP (Ready for Planning): At the end of the Initiating Phase
  RfE (Ready for Executing): At the end of the Planning Phase
  RfC (Ready for Closing): At the end of the Executing Phase
Archived
Initiating
Planning
Executing
Closing
RfP
RfE
RfC

## Slide 27: PM² Phases & Activities & Artefacts
- Document the idea/need
- Identify key stakeholders (and their needs)
- Create a business justification for the project
- Define the project scope and organisation
Initiating
Project Initiation Request
Business Case
Project Charter
Project Logs (setup).
Ready for Planning
- Organise a Kick-off Meeting
- Tailor the PM² process
- Assign roles & responsibilities
- Elaborate project scope
- Develop work breakdown & project schedule
- Develop project plans
- Distribute plans to stakeholders
Planning
Planning Kick-off/ MoM
Project Handbook
- Roles & responsibilities
- Management plans
- Requirements management
Project Stakeholder Matrix
Outsourcing Plan
Project Work Plan
Deliverables Acceptance Plan
Transition Plan
Business Implementation Plan
Ready for Executing
- Organise a Kick-off Meeting
- Coordinate project execution
- Conduct Meetings
- Assure Quality
- Create Project reports
- Distribute information
- Ensure deliverables acceptance
Executing
Executing Kick-Off/MoM
Meeting Agendas/MoMs
Project Progress Report
Project Status Reports
Quality Review Report
Change Requests
Deliverables Acceptance Note
Ready for Closing
- Organise a Project-End Review Meeting
- Capture lessons learned and post-project recommendations
- Get final project acceptance
- Release project resources
- Archive project information
Closing
Project-End Review Agenda/ MoM
Project-End Report
- Lessons Learned
- Best Practices
- Post Project Recommendations
Project Acceptance Note
Monitor & Control
- Monitor Project Performance
- Control Schedule
- Control Cost
- Manage Quality
- Manage Requirements
- Manage Project Change
- Manage Risks
- Manage Issues and Decisions
- Manage Stakeholders
- Manage Deliverables Acceptance
- Manage Transition
- Manage Business Implementation
- Manage Outsourcing
Activities
Regularly updated
Risk Log
Issue Log
Decision Log
Change Log
Project Work Plan
Requirements Document
Checklists
Phase-exit Review Checklist
Quality Review Checklist
Deliverables Acceptance Checklist
Transition Checklist
Business Implementation Checklist
Stakeholder Checklist
Artefacts
RfP
RfE
Activities
Artefacts
RfC

## Slide 28: The PM² Artefacts Landscape
Initiating
Project Initiation
Request
Business Case
Project Charter
Planning
MANAGEMENT PLANS
Project Change
Management
Plan
Requirements
Management
Plan
Risk
Management
Plan
Quality
Management
Plan
Issue
Management
Plan
Communications
Management
Plan
Project Handbook
Project
Stakeholder Matrix
Project Work Plan
Business
Implementation
Plan
Transition Plan
Outsourcing
Plan
Deliverables
Acceptance
Plan
Executing
PROJECT REPORTS
Quality Review
Report
Project Status
Report
Project Progress
Report
Change
Request Form
Minutes
Of Meetings
Meetings
Agendas
MEETING DOCS
Closing
Project-End
Report
Monitor & Control
PROJECT LOGS
Decision Log
Risk Log
Change Log
Issue Log
Project Work
Plan (updates)
CHECKLISTS
Phase-exit
Review Checklist
Deliverables
Acceptance
Checklist
Transition Checklist
Quality
Review Checklist
Business Implementation
Checklist
Stakeholders
Checklist

## Slide 29: Tailoring
First, understand purpose and value of the PM² methodology
Don’t cut, but customise
Balance control gained against effort required
Eliminate waste, but respect the integrity of the method

## Slide 30: The purpose of documentation is to…
Help people think something through
Provide a clear picture of the project requirements.
Facilitate communication.
Facilitate agreement by all project stakeholders.
Offer a baseline for the monitoring & controlling.
Document important decisions made (and track changes).
Respond to Audit requirements.
Integrate new-team members.
Support organizational memory.
Support maintenance

## Slide 31: The Expanding Reach of PM²
PM² v1.0
DIGIT
(IT Projects)
PM² v2.0
European
Commission
PM² v2.5
European
Institutions
EU Agencies
European Council
European Financial Institutions
Open PM²
v1.0
EU Member
States
EU Grants Beneficiaries
EU Contractors
Public
Sector
Private Sector
V3.1
European
Europe & the World

## Slide 32: The PM² Guide & Artefacts – V3.1
The PM2 Project Management Methodology Guide & Artefacts v3.1
AVAILABLE via Web: https://pm2.europa.eu/index_en

## Slide 33: Project Governance

## Slide 34: A PM² Project
Is (above all) a project (i.e. not operations, not a work activity, not a programme etc.).
has a duration of more than 4–5 weeks and involves more than 2–3 people.
runs within an organisation and can be subject to internal or external audits.
requires a clearly defined governance structure and clearly assigned roles and responsibilities.
requires approval of its budget and scope.
includes more than just construction/delivery activities.
includes transition and business implementation activities.
requires a certain level of documentation, transparency and reporting.
requires a certain level of control and traceability.
has a broad base of internal (and external) stakeholders.
may require the collaboration of several organisations or organisational units.
Contributes to raising the organisation’s project management maturity.

## Slide 35: The PM² Governance Model

## Slide 36: The Project Owner (PO) Role
Acts as the project sponsor, promotes the project’s success
Provides leadership and strategic direction
Chairs the Project Steering Committee (PSC)
Accepts the business objectives
Coordinates the resolution of escalated issues and conflicts
Monitors project progress regularly (high level)
Mobilises resources (a.k.a. budget)
Assures that project outcomes are in line with the business objectives
Drives organisational change and monitors proper evolution and change implementation
Approves all key management Artefacts

## Slide 37: The Solution Provider (SP) Role
Assumes the overall accountability for project deliverables/services requested by the Project Owner (PO)
Represents the interests of those designing, developing, facilitating, procuring, implementing, and possibly operating and maintaining the project outputs (e.g. IT System)
Agrees on objectives for the provider activities and approves the deliverables for the project
Mobilises the needed resources from the provider side and appoints the PM
Approves the objectives of any outsourced activities and deliverables and becomes accountable for the contractor’s performance

## Slide 38: The Business Manager (BM) Role
Acts on a daily basis on behalf of the Project Owner (PO)
Guarantees cooperation and an efficient communication channel with the Project Manager (PM)
Drives the definition of business and project objectives
Manages the activities on the business side of the project and ensures that the required business resources are made available
Coordinates the Business Implementation Group (BIG) and acts as a liaison between the User Representatives (URs) and the provider organisation
Ensures that the project outputs produce the expected results (outcomes and benefits)
Ensures that the client organisation is ready to accommodate and use the final project outputs
Leads the implementation of the business changes within the user community

## Slide 39: The Project Manager (PM) Role
Executes the project plans as approved by the Project Steering Committee (PSC)
Daily manages and coordinates the Project Core Team (PCT) activities and resources
Ensures that project objectives are achieved within the quality, time, and cost objectives
Manages stakeholder's expectations
Ensures that all key management artefacts are delivered and approved by the Project Owner (PO) or the Project Steering Committee (PSC)
Ensures the controlled evolution of delivered outputs, through proper change management
Performs risk management activities for project-related risks
Escalates unresolvable project issues to the Project Steering Committee (PSC).
Monitors and reports project status and progress to the Project Steering Committee (PSC)
Liaises between the Directing and Performing Layers of the project

## Slide 40: Project Steering Committee (PSC)

## Slide 41: PM² Artefacts & Activities Overview RAM (RASCI)
Project Steering Committee: accountable for the Project Work Plan?
Project Owner: almost full accountability
Project Manager: does the work but is NOT accountable

## Slide 42: Summary – Roles & Responsibilities
The PM² Governance – Roles & Responsibilities
The Project Steering Committee (PSC)
The Project Core Team (PCT)
Differences between Project Mode and Service Mode
The Responsibility Assignment Matrix - RAM (RASCI)

## Slide 43: PM2 Mindsets

## Slide 44: The PM2 Mindsets
Apply PM² best practices to manage their projects.
Remain mindful that PM methodologies are there to serve projects and not the other way around.
Maintain an outcomes orientation in relation to all projects and project management activities.
Are committed to delivering project results with maximum value rather than just following plans.
Foster a project culture of collaboration, clear communication and accountability.
Assign project roles to the most appropriate people for the benefit of the project.
Balance in the most productive way the often-conflicting project management “Ps” of: product, purpose, process, plan, people, pleasure/pain, participation, perception and politics.
Invest in developing technical and behavioural competences to become better project contributors.
Involve project stakeholders in the organisational change needed to maximise project benefits.
Share knowledge, actively manage Lessons Learned, and contribute to the improvement of project management within their organisations.
Draw inspiration from the PM² Guidelines on Ethics and Professional Virtues.
The PM2 Mindsets are reminders of effective behaviors and attitudes. They provide a common set of beliefs and values for all PM2 teams, helping them navigate through the complexities of project reality.

## Slide 45: PM² Mindsets: IAQs (Questions for the Brave!)
Project Managers and Project Teams who practice PM² also ask the important questions:
Do we know what we are doing?
  Tip: Develop a clear and shared project vision. Manage the project using a holistic approach and optimise the whole project, not just parts of it. Follow a process but stay Agile and try to regularly remind yourself why you are doing something.
Do we know why we are doing it? Does anyone really care?
  Tip: Make sure your project matters. Understand its goals, value and impact, and how it relates to the organisational strategy. Define upfront what project success is and deliver maximum value and real benefits, not just outputs.
Are the right people involved?
  Tip: People make projects work. The primary criterion for involving people and assigning project roles should be to serve the needs and objectives of the project, and not politics, friendship, functional hierarchy, proximity or convenience.
Do we know who is doing what?
  Tip: Know what you should be doing, and make sure others know what they should be doing. Is it clear to everyone? Clearly define and understand roles, responsibilities and accountabilities.
Deliver at any cost or risk?
  Tip: Show respect for people’s work and organisational funds and avoid high-risk behavior and tactics. Always keep in mind that it is not just about the end result – how you get there also matters. Manage your projects based on positive values and principles.

## Slide 46: PM² Mindsets: IAQs (Questions for the Brave!)
… and continue asking important questions:
Is this important?
  Tip: Everything is NOT equally important. Identify, and agree on, the project’s Critical Success Criteria (CSC), Minimum Viable Product and Critical Success Factors (CSFs), and allocate effort and attention both tactically and strategically for the benefit of both the project and project management goals.
Is this a task for “them” or for “us”?
  Tip: Make sure that client and provider groups work as one team towards a common goal. Real teamwork really works; so foster clear, effective and frequent communication.
Should I be involved?
  Tip: Contribute from any position. Be proud of the skills, value and positive attitude you bring to the project. Help everyone who needs to be involved get involved. Promote and facilitate the contributions of all stakeholders.
Have we improved?
  Tip: Commit to ongoing self- and organisational improvement by gathering and sharing knowledge. Project teams should reflect on how they can become more effective and adjust their behavior accordingly.
Is there life after the project?
  Tip: The product (or service) lifecycle has just begun! Make sure you have contributed to its success.

## Slide 47: Bringing it all Together: Processes + Mindsets
Help us make decisions on trade-offs between project dimensions of time, cost, scope and quality
PM2
Processes & Artefacts
The attitudes and behaviours which help us focus on what is really important in achieving our project goals
PM2 Mindsets
Together
They help us navigate the complexities of managing projects in organisations and make PM² both more effective and complete

## Slide 48: Phases and Artefacts

## Slide 49: Initiating Phase
Initiating

## Slide 50: What happens in the Initiating Phase?
Initiating
Set the project objectives.
Get the business justification.
Make the preliminary planning.
Start the project documentation.
Idea / Need
Document the idea/need
Project Initiation Request
Identify key stakeholders
(and their needs)
Create a business justification for the project
Business Case
Define the project scope
& organisation
Project Charter
RfP (Ready for Planning)

## Slide 51: Initiating Phase: The PM² Artefacts Landscape
Initiating Phase
Project-End
Report
PROJECT LOGS
Decision Log
Risk Log
Change Log
Issue Log
Project Handbook
Project
Stakeholder Matrix
Project Work Plan
Business
Implementation
Plan
Transition Plan
Project Work
Plan (updates)
CHECKLISTS
Phase-exit
Review Checklist
Deliverables
Acceptance
Checklist
Transition Checklist
Quality
Review Checklist
MANAGEMENT PLANS
Business Implementation
Checklist
Stakeholders
Checklist
Project Change
Management
Plan
Requirements
Management
Plan
Risk
Management
Plan
Quality
Management
Plan
Issue
Management
Plan
Communications
Management
Plan
Outsourcing
Plan
Deliverables
Acceptance
Plan
PROJECT REPORTS
Quality Review
Report
Project Status
Report
Project Progress
Report
Change
Request Form
Minutes
Of Meetings
Meetings
Agendas
MEETING DOCS
Initiating
Planning
Executing
Closing
Monitor & Control
Project Initiation
Request
Business Case
Project Charter

## Slide 52: Project Initiation Request (TOC)
Initiating Phase
Purpose
Ensure that the problem/need/opportunity as well as project concept is captured in writing.
R: BM S: PO, UR
A: PO
Problem, need
or opportunity
Project Initiation Request
RASCI
RAM (RASCI) | AGB | PSC | PO | BM | BIG | SP | PM | PCT
Project Initiation Request | I | N/A | A/S | R | S/C | I | N/A | N/A

## Slide 53: Project Initiation Request
Initiating Phase

## Slide 54: Business Case
Initiating Phase
Purpose
Captures the reasoning for the project.
Provides the justification for the project and establishes its budgetary constraints.
Provides information to determine whether the project should move ahead or not.
R: BM S: SP, PM
A: PO
Business Case
Project Initiation
Request
RAM (RASCI) | AGB | PSC | PO | BM | BIG | SP | PM | PCT
Business Case | I | C | A | R | C | S | S | N/A
RASCI

## Slide 55: Initiating Phase: Business Case
Initiating Phase

## Slide 56: Project Charter
Initiating Phase
Purpose
The key element of the project approval process (along with the Business Case).
Provides a basis for the more detailed project planning.
It includes the What, How and When fundamentals of the project.
RASCI
RAM (RASCI) | AGB | PSC | PO | BM | BIG | SP | PM | PCT
Project Charter | I | A | C | S | C | S | R | C

## Slide 57: Initiating Phase: Project Charter
Initiating Phase

## Slide 58: Initiating Documents Strategy
Initiating Phase
Business Case
Project Initiation Request
Initiating
Planning
Project Charter
Domain Specific Content (if required)

## Slide 59: Phase Gate: RfP (Ready for Planning)?
Initiating Phase
Archived
Initiating
Planning
Executing
Closing
RfP
RfE
RfC

## Slide 60: Planning Phase
Planning Phase
Monitor & Control
Artefacts
Ready for Executing
Initiating
Executing
Closing
Monitor & Control
Planning
RfE
Planning Kick-off/ MoM
Project Handbook
- Roles & responsibilities
- Management plans
- Requirements management
Project Stakeholder Matrix
Project Work Plan
Transition Plan
Business Implementation Plan

## Slide 61: What happens in the Planning Phase?
Planning Phase
RfP (Ready for Planning)
Kick-Off meeting
Kick-Off Agenda & MoM
Tailor the PM² process
Project Handbook
&
Management Plans
Assign roles &
responsibilities
Project Stakeholder Matrix
Elaborate project scope
Project Handbook
Develop work breakdown and project schedule
Project
Work Plan
Develop the project plans
All Project Plans
Distribute plans
to stakeholders
RfE (Ready for Executing)
Develop the project scope statement.
Determine the project approach and main activities.
Develop the schedule for the various tasks and estimate the necessary resources.
Assign roles and responsibilities.
Develop the Project Handbook and various project plans for the project.

## Slide 62: Planning Phase: The PM² Artefacts Landscape
Planning Phase
Project-End
Report
PROJECT LOGS
Decision Log
Risk Log
Change Log
Issue Log
Project Initiation
Request
Business Case
Project Charter
Project Handbook
Project
Stakeholder Matrix
Project Work Plan
Business
Implementation
Plan
Transition Plan
Project Work
Plan (updates)
CHECKLISTS
Phase-exit
Review Checklist
Deliverables
Acceptance
Checklist
Transition Checklist
Quality
Review Checklist
MANAGEMENT PLANS
Business Implementation
Checklist
Stakeholders
Checklist
Project Change
Management
Plan
Requirements
Management
Plan
Risk
Management
Plan
Quality
Management
Plan
Issue
Management
Plan
Communications
Management
Plan
Outsourcing
Plan
Deliverables
Acceptance
Plan
PROJECT REPORTS
Quality Review
Report
Project Status
Report
Project Progress
Report
Change
Request Form
Minutes
Of Meetings
Meetings
Agendas
MEETING DOCS
Initiating
Planning
Executing
Closing
Monitor & Control

## Slide 63: Project Handbook (1)
Planning Phase
Purpose
Summarizes the project objectives.
Documents the overall project management approach and tailoring.
Defines the key controlling processes, the project policies and rules.
It becomes the basis for managing the project throughout its lifecycle as an important point of reference.
A: PO
R: PM S: BM
Project Handbook
Project Charter
Business Case
Planning Kick-Off
Meeting Minutes
RASCI
RAM (RASCI) | AGB | PSC | PO | BM | BIG | SP | PM | PCT
Project Handbook | I | I | A | S | C | I | R | C

## Slide 64: Project Handbook (2)
Planning Phase

## Slide 65: Project Stakeholder Matrix (1)
Planning Phase
Purpose
Lists all (key) project stakeholders and their contact details and clearly states their role(s) in the project.
It may also include a classification or categorisation of each stakeholder
A: PO
R: PM S: BM
Project Stakeholder Matrix
Project Charter
Business Case
Planning Kick-Off
Meeting Minutes
RASCI
RAM (RASCI) | AGB | PSC | PO | BM | BIG | SP | PM | PCT
Project Stakeholder Matrix | I | I | A | S | C | I | R | C

## Slide 66: Project Stakeholder Matrix (2)
Planning Phase

## Slide 67: Project Work Plan (1)
Planning Phase
Purpose
Identifies and organises the project into activities, sub-tasks, and work packages.
Establishes a base to estimate the duration of the project.
Determines the required resources and schedules the work.
It is used as the basis to monitor the progress and control the project.
A: PSC
R: PM S: BM, PCT
Work Breakdown
Project Schedule
Effort & Costs
Estimates
Business Case
Project Charter
Project Work Plan
RASCI
RAM (RASCI) | AGB | PSC | PO | BM | BIG | SP | PM | PCT
Project Work Plan | I | A | C | S/C | C | C | R | S/C

## Slide 68: Project Work Plan (2)
Planning Phase

## Slide 69: Planning: The PM² Management Plans
Planning Phase
Risk Management Plan
Issue Management Plan
Requirements Management Plan
Project Change Management Plan
Quality Management Plan
Communications Management Plan
Part of the Project Handbook
Or standalone

## Slide 70: Communications Management Plan
Planning Phase
Purpose
Ensures that the Project Core Team and all the Project Stakeholders will have the information they need to perform their roles throughout the project.
Defines and documents communication activities, their goals, content, format, frequency and audience with both the performing and the participating organisation.
A: PO
S: BM R: PM
Communications
Management
Plan
Project Handbook
Project Charter
Project Charter
&
Business Case
Project Stakeholder Matrix
Project Handbook
&
Project Work Plan
RASCI
RAM (RASCI) | AGB | PSC | PO | BM | BIG | SP | PM | PCT
Communication Management Plan | I | I | A | S | C | I | R | C

## Slide 71: Transition Plan
Planning Phase
Purpose
Ensures a controlled and smooth transition from the old state to the new state in which the new product/service developed by the project is put in place.
RASCI
RAM (RASCI) | AGB | PSC | PO | BM | BIG | SP | PM | PCT
Transition Plan | I | A | C | C | C | C | R | C

## Slide 72: Business Implementation Plan
Planning Phase
Purpose
All business implementation activities are critical for smooth operations.
Business implementation activities are complementary to transition activities.
Outlines the impact of the project on the organisation.
Defines the change management activities that permanent organisation need to carry out, usually as part of ongoing operations or future projects (post-actual project activities).
RASCI
RAM (RASCI) | AGB | PSC | PO | BM | BIG | SP | PM | PCT
Project Work Plan | I | I | A | R | C | I | S | I

## Slide 73: Outsourcing Plan
Planning Phase
Purpose
Outlines the scope of products and/or services to be contracted outside the organisation.
Defines the time, cost and quality expectations from the Contractor’ organisation.
Identifies responsibilities for the full contract lifecycle (the Project Manager, procurement group, the Contractor’s organisation, etc.)
RASCI
RAM (RASCI) | AGB | PSC | PO | BM | BIG | SP | PM | PCT
Outsourcing Plan | A | C | C | C | I | S | R | I

## Slide 74: RfE (Ready for Executing)?
Planning Phase
Archived
Initiating
Planning
Executing
Closing
RfE
RfP
RfC

## Slide 75: Executing Phase
Executing Phase
Artefacts
Ready for Closing
Initiating
Planning
Closing
Monitor & Control
Executing
RfC
Executing Kick-Off/MoM
Meeting Agendas/MoMs
Project reports
Change Requests
Deliverables Acceptance Note

## Slide 76: What happens in the Executing Phase
Executing Phase
RfE (Ready for Executing)
Kick-Off meeting
Kick-off
Agenda & MoM
Coordinate project
Meetings Agendas and MOMs
Meetings Agendas/MoMs
Audit reports
Project reports
Deliverables
Acceptance Note
RfC (Ready for Closing)
Ensure deliverables acceptance
Distribute information
Assure quality
Create project reports
Conduct meetings
  Coordinate the project work, people and resources.
  Execute various project plans.
  Report on the project progress and status.
  Produce the project deliverables.
  Prepare for their reception (the requestor organisation).

## Slide 77: Executing Phase: The PM² Artefacts Landscape
Executing Phase
Project-End
Report
PROJECT LOGS
Decision Log
Risk Log
Change Log
Issue Log
Project Initiation
Request
Business Case
Project Charter
Project Handbook
Project
Stakeholder Matrix
Project Work Plan
Business
Implementation
Plan
Transition Plan
Project Work
Plan (updates)
CHECKLISTS
Phase-exit
Review Checklist
Deliverables
Acceptance
Checklist
Transition Checklist
Quality
Review Checklist
MANAGEMENT PLANS
Business Implementation
Checklist
Stakeholders
Checklist
Project Change
Management
Plan
Requirements
Management
Plan
Risk
Management
Plan
Quality
Management
Plan
Issue
Management
Plan
Communications
Management
Plan
Outsourcing
Plan
Deliverables
Acceptance
Plan
PROJECT REPORTS
Quality Review
Report
Project Status
Report
Project Progress
Report
Change
Request Form
Minutes
Of Meetings
Meetings
Agendas
MEETING DOCS
Initiating
Planning
Executing
Closing
Monitor & Control

## Slide 78: Project Coordination
Executing Phase
Purpose
Facilitates the project’s progress by continuously providing information to the Project Core Team (PCT) and supporting the completion of assigned work;
Includes allocating project resources to activities, performing regular quality checks of interim results, maintaining ongoing communication with all project team members, and keeping everyone involved in the project motivated through leadership, negotiations, conflict resolution
A: PO
Project Handbook
Project Work Plan
Signed-off work assignments
R: PM S: BM
RASCI
RAM (RASCI) | AGB | PSC | PO | BM | BIG | SP | PM | PCT
Project Coordination | I | I | A | S | I | I | R | I

## Slide 79: Project Reporting
Executing Phase
Purpose
Communicates consolidated information concerning project performance to the appropriate stakeholders, enabling decision-making.
Typically provides information on scope, schedule, effort/cost and quality, the status of risks, issues, project changes and outsourcing.
May also contain agreed project indicators and metrics for evaluating progress.
A: PO
R: PM S: BM
Project Work Plan
Project Reports
Transition Plan &
Business Implementation Plan
Project Work Plan
Communications Management Plan
Project Handbook
Project Charter
&
Business Case
Project Logs
&
Project Checklists
RASCI
RAM (RASCI) | AGB | PSC | PO | BM | BIG | SP | PM | PCT
Project Reporting | I | I | A | S/C | I/C | I/C | R | C

## Slide 80: PM² Project Reports
Executing Phase
Project Progress Report
Project Status Report

## Slide 81: Information Distribution
Executing Phase
Purpose
Keeps project stakeholders informed about relevant project details through the regular distribution of project reports, as per the Communications Management Plan and project stakeholder needs
A: PO
R: PM
Communications
Management
Plan
Project Work Plan
Minutes of Meeting
(MoM)
Project Charter
&
Business Case
Project Reports
&
Project Logs
Information Distribution
RASCI
RAM (RASCI) | AGB | PSC | PO | BM | BIG | SP | PM | PCT
Project Reporting | I | I | A | C | I | I | R | C

## Slide 82: Quality Assurance
Executing Phase
Purpose
Gathers evidence that proves the project work is following high-quality standards, methodologies and best practices.
Describes in the Quality Management Plan and executes the relevant activities.
Includes determining whether appropriate project controls are in place, confirming that they are being implemented and assessing their effectiveness.
A: PM
R: PCT S: BM
Project Logs (updated)
Quality Management Plan
Project Work Plan
Project Outline
Audit Reports
RASCI
RAM (RASCI) | AGB | PSC | PO | BM | BIG | SP | PM | PCT
Quality Assurance | I | I | I | S | C | I | A | R

## Slide 83: Monitor & Control
Monitor & Control

## Slide 84: What happens during Monitor & Control
Monitor & Control
  All work is observed from the point of view of the Project Manager. The key activities:
Manage:
Execute all management processes defined in the Project Management Plans, and manage the outsourcing, transition, business implementation and deliverables acceptance activities as per the relevant Project Specific Plans.
Monitor:
Monitor project activities and overall project performance.
Track the project performance against the baseline to facilitate reporting and controlling.
Control:
Devise, plan, propose and implement corrective actions to address existing or potential performance risks or issues, while updating the relevant project plans and logs.

## Slide 85: Monitor & Control Activities
Monitor & Control
  Monitor Project Performance
  Control Schedule
  Control Cost
  Manage Stakeholders
  Manage Requirements
  Manage Project Change
  Manage Risks
  Manage Issues and Decisions
  Manage Quality
  Manage Deliverables Acceptance
  Manage Transition
  Manage Business Implementation
  Manage Outsourcing

## Slide 86: Monitor Project Performance
Monitor & Control
Purpose
Collects information about the state of the project’s progress and overall health.
Tracks the project dimensions of scope, schedule, cost and quality, monitors risks, issues and project change, and forecasts their evolution for the purpose of reporting the overall project progress to relevant stakeholders as per the Communications Management Plan.
A: PO
R: PM
Project Work Plan
Project Work Plan
(tracked)
Project Work Plan
(baselined)
Quality Checklist
Project Handbook
Project Charter
&
Business Case
Project Logs
&
MoMs
RASCI
RAM (RASCI) | AGB | PSC | PO | BM | BIG | SP | PM | PCT
Monitor Project Performance | I | I | A | C | C | I | R | C

## Slide 87: Control Schedule
Monitor & Control
Purpose
Ensures that project tasks are carried out as scheduled and that project deadlines are met.
Regularly monitors the schedule and tracks the difference between planned, actual and forecast activities/deadlines.
Informs the Project Steering Committee (PSC) about any risks for the schedule for the informed decision-making.
A: PO
R: PM
Project Work Plan
Project Logs
(updated)
Transition Plan &
Business Implementation Plan
Project Work Plan
Change Log
Project Handbook
Project Charter
&
Business Case
MoMs
&
Project Reports
Project Work Plan
(updated)
RASCI
RAM (RASCI) | AGB | PSC | PO | BM | BIG | SP | PM | PCT
Control Schedule | I | I | A | C | C | I | R | C

## Slide 88: Cost Control
Monitor & Control
Purpose
Manages the project costs so that they conform to the cost/effort baseline and overall project budget constraints.
Regularly monitors the budget and tracks the difference between budgeted, actual and expected costs.
Informs the Project Steering Committee (PSC) about any risks for the schedule for the informed decision-making.
A: PO
R: PM
Project Work Plan
Project Logs
(updated)
Transition Plan &
Business Implementation Plan
Project Work Plan
Outsourcing Plan & Change Log
Project Handbook
Project Charter
&
Business Case
MoMs
&
Project Reports
Project Work Plan
(updated)
RASCI
RAM (RASCI) | AGB | PSC | PO | BM | BIG | SP | PM | PCT
Control Cost | I | I | A | C | C | I | R | C

## Slide 89: Manage Stakeholders
Monitor & Control
Project stakeholders are people (or groups) who can affect or can be affected by both the activities performed during the life of a project, or/and by the project’s output(s) and outcome(s).
Purpose
Identifies project stakeholders, captures their project expectations and requirements.
Defines communication strategy and performs activities to communicate with stakeholders throughout project lifecycle and encourages them to get involved and contribute.
Monitors and captures stakeholders' overall project experience and satisfaction.
Issue and Decision Logs
Project Handbook
& Stakeholder Matrix
Deliverable Acceptance &
Transitions Plans
Issue and Decision Logs
Stakeholder Matrix
(updated)
Project Handbook
& Stakeholder Matrix
Deliverable Acceptance &
Transitions Plans
Communications Management Plan
Business Implementation Plan
A: PO
R: PM S: BM
Stakeholder Checklist
RASCI
RAM (RASCI) | AGB | PSC | PO | BM | BIG | SP | PM | PCT
Manage Stakeholders | I | I | A | S/C | I | C | R | I

## Slide 90: Manage Requirements
Monitor & Control
Purpose
Gathers, documents and validates requirements, and manages their implementation and change.
Runs throughout the project lifecycle and relates to other project management processes, such as quality and change management.
Requirements Management Plan
Project Charter
&
Project Handbook
Business Case &
Project Charter
Project Stakeholder Matrix
Project Work Plan
A: PO
R: PM S: PCT
Requirements Document
Project Work Plan
(updated)
Project Logs
(updated)
RASCI
RAM (RASCI) | AGB | PSC | PO | BM | BIG | SP | PM | PCT
Manage Requirements | I | I | A | C | C | I | R | S

## Slide 91: Monitor & Control: Manage Requirements
Monitor & Control

## Slide 92: Manage Project Change (1)
Monitor & Control
Purpose
Identifies, documents, assesses, prioritises, approves, plans and controls project changes, and communicats them to all relevant stakeholders.
Changes can be requested (or identified and raised) throughout the project lifecycle by any project stakeholder and can be related to a change in the project scope, requirements, deliverables and features, or quality characteristics of the project.
Project Change Management Plan
Project Work Plan
Communications Management Plan
Project Charter
&
Project Handbook
Business Case
&
Project Charter
A: PO
Change Request Form
Change Log (updated)
Project Work Plan (updated)
R: PM S: BM
RASCI
RAM (RASCI) | AGB | PSC | PO | BM | BIG | SP | PM | PCT
Manage Project Changes | I | C | A | S | I | I | R | C

## Slide 93: Manage Project Change (2)
Monitor & Control

## Slide 94: Manage Risk (1)
Monitor & Control
Purpose
Identifies, assesses and manages risks so that they conform to the organisation’s accepted risk attitude.
Improves the project team’s confidence by proactively managing any potential event that might have a positive or negative impact on project objectives.
A risk is an uncertain event or set of events (positive or negative) that, should it occur, will have an impact on the achievement of project objectives.
Project Charter
&
Project Handbook
Business Case
&
Project Charter
Risk Log
A: PO
R: PM S: BM
Risk Log
(updated)
Risk
Management
Plan
RASCI
RAM (RASCI) | AGB | PSC | PO | BM | BIG | SP | PM | PCT
Manage Risk | I | C | A | S/C | C | I | R | C

## Slide 95: Manage Risk (2)
Monitor & Control

## Slide 96: Manage Issues & Decisions (1)
Monitor & Control
Purpose
Identifies, evaluates and manages issues for resolution by project stakeholders, and decisions are taken, documented and implemented.
Issues and decisions are often linked to the resolution of other log items (e.g. risks, changes).
An issue is an immediate problem requiring resolution. Anyone can raise issues. It is always important to solve the root cause, not the symptom. This will ensure that the problem will not re-occur.
A: PO
R: PM S: BM
Issue Log
(updated)
Decision Log
(updated)
Issue
Management Plan
Issue
Management
Plan
MoMs
Project Logs
RASCI
RAM (RASCI) | AGB | PSC | PO | BM | BIG | SP | PM | PCT
Manage Issues & Decisions | I | I | A | S | C | I | R | C

## Slide 97: Manage Issues & Decisions (2)
Monitor & Control

## Slide 98: Manage Quality
Executing

## Slide 99: Manage Deliverable Acceptance
Monitor & Control
Purpose
Ensures project deliverables are based on predefined objectives and set of criteria as defined in the Deliverables Acceptance Plan.
The final project acceptance takes place in the Closing Phase.
RASCI
RAM (RASCI) | AGB | PSC | PO | BM | BIG | SP | PM | PCT
Manage Deliverable Acceptance | I | I | A | S | C | C | R | C

## Slide 100: Manage Transition
Monitor & Control
Purpose
Ensures a controlled and smooth transition from the old state to the new state in which the new product/service developed by the project is put in place.
Ensures the correct transfer of project deliverables to the project requestor organisation.
RASCI
RAM (RASCI) | AGB | PSC | PO | BM | BIG | SP | PM | PCT
Manage Transition | I | A | C | C | C | C | R | C

## Slide 101: Manage Business Implementation
Monitor & Control
Purpose
Executes all business implementation activities, critical for smooth operations, even after the project’s outputs have been delivered to the stakeholder/user community.
A good practice to also define some post-project change activities, however, their implementation falls outside the domain of responsibilities of the project.
Business Implementation Plan
Project Handbook
Transition Plan
Project Work Plan
A: PO
R: BM S: PM
Business Implementation Checklist
Project Work Plan
(updated)
RASCI
RAM (RASCI) | AGB | PSC | PO | BM | BIG | SP | PM | PCT
Manage Business Implementation | I | I | A | R | C | I | S | I

## Slide 102: Manage Outsourcing
Monitor & Control
Purpose
Ensures that the Contractor delivers acceptable quality of work as defined in the Outsourcing Plan.
This work is undertaken by the Project Manager (PM) in conjunction with the relevant procurement groups and the Contractor’s Project Manager (CPM).
A: AGB
R: PM S: SP
Business Case
Project Charter
Project Outline
Signed
Purchase Order(s)
Project Outline
Signed
Timesheet(s)
Project Outline
Signed
Contract(s)
Project Outline
Status &
Progress
Report(s)
Project Work Plan
Outsourcing Plan
RASCI
RAM (RASCI) | AGB | PSC | PO | BM | BIG | SP | PM | PCT
Manage Outsourcing | A | C | C | C | I | S | R | I

## Slide 103: Monitor & Control Artefacts
Monitor & Control
Project-End
Report
PROJECT LOGS
Decision Log
Risk Log
Change Log
Issue Log
Project Initiation
Request
Business Case
Project Charter
Project Handbook
Project
Stakeholder Matrix
Project Work Plan
Business
Implementation
Plan
Transition Plan
Project Work
Plan (updates)
CHECKLISTS
Phase-exit
Review Checklist
Deliverables
Acceptance
Checklist
Transition Checklist
Quality
Review Checklist
MANAGEMENT PLANS
Business Implementation
Checklist
Stakeholders
Checklist
Project Change
Management
Plan
Requirements
Management
Plan
Risk
Management
Plan
Quality
Management
Plan
Issue
Management
Plan
Communications
Management
Plan
Outsourcing
Plan
Deliverables
Acceptance
Plan
PROJECT REPORTS
Quality Review
Report
Project Status
Report
Project Progress
Report
Change
Request Form
Minutes
Of Meetings
Meetings
Agendas
MEETING DOCS
Initiating
Planning
Executing
Closing
Monitor & Control

## Slide 104: Logs
Monitor & Control

## Slide 105: Summary – Monitor & Control
Monitor & Control
Monitor project performance
Control Project variables (compared to plans)
Use Project Logs to control the project
Execute Project Management Plans and related activities
Take corrective actions -> update plans

## Slide 106: RfC (Ready for Closing)?
Executing
Archived
Initiating
Planning
Executing
Closing
RfE
RfP
RfC

## Slide 107: Closing Phase
Closing
Artefacts
Project-End Review Agenda/ MoM
Project-End Report
- Lessons Learned
- Best Practices
- Post Project Recommendations
Project Acceptance Note
Initiating
Planning
Executing
Monitor & Control
Closing

## Slide 108: What happens in the Closing Phase
Closing
Finalise all project activities.
Document project’s final state.
Discuss and capture Lessons Learned and Best Practices, and post-project recommendations.
Accept project deliverables.
Formally close the project.
End of Project
RfC (Ready for Closing)
Project-End Review Agenda/MoM
Project-End Report
Project Acceptance Note (if required)
Project-End Review Meeting
Capture lessons Learned & Post-Project Recommendations
Final project acceptance
Release resources
Archive project
Projects Archive

## Slide 109: Closing Phase: The PM² Artefacts Landscape
Closing
Project-End
Report
PROJECT LOGS
Decision Log
Risk Log
Change Log
Issue Log
Project Initiation
Request
Business Case
Project Charter
Project Handbook
Project
Stakeholder Matrix
Project Work Plan
Business
Implementation
Plan
Transition Plan
Project Work
Plan (updates)
CHECKLISTS
Phase-exit
Review Checklist
Deliverables
Acceptance
Checklist
Transition Checklist
Quality
Review Checklist
MANAGEMENT PLANS
Business Implementation
Checklist
Stakeholders
Checklist
Project Change
Management
Plan
Requirements
Management
Plan
Risk
Management
Plan
Quality
Management
Plan
Issue
Management
Plan
Communications
Management
Plan
Outsourcing
Plan
Deliverables
Acceptance
Plan
PROJECT REPORTS
Quality Review
Report
Project Status
Report
Project Progress
Report
Change
Request Form
Minutes
Of Meetings
Meetings
Agendas
MEETING DOCS
Initiating
Planning
Executing
Closing
Monitor & Control

## Slide 110: Wrap-up

## Slide 111: Course End: Lessons Learned (& Shared)
What are your top 3 learnings?
Which aspects of this course were delivered effectively?
How can this course be improved?

## Slide 112: You are using PM² for your project? We would like to hear about it! Contact Us